## Slide 1
EEM P&L Reconciliation Deloitte Proposal – September 2026

## Slide 2
01. | Executive Summary
02. | Solution Approach
03. | Project Setup
04. | Expected Challenges and Risks
05. | Deloitte References & Case Examples
06. | Commercials
07. | Appendix: CVs

## Slide 3
01. | Executive Summary
02. | Solution Approach
03. | Project Setup
04. | Expected Challenges and Risks
05. | Deloitte References & Case Examples
06. | Commercials
07. | Appendix: CVs

## Slide 4: E.ON’s current situation and project objectives
Initial Situation
Objectives
E.ON Energy Markets GmbH (EEM), acts as a central interface to the wholesale markets. The main function is to consolidate and optimize E.ON’s commodity positions, to reduce price risks from the distribution business and to diversify and reduce credit and margin risks.
In 2020 EEM’s power and gas portfolio consisted of 500 TWh delivery rights to more than 40 million customers in Europe
A small number of proprietary trading transactions are entered into in separate trading books, which are subject to strict monitoring and limits based on risk metrics and governance. The processes and operational management models within the trading system are monitored by the local market risk teams and centrally managed by the Risk Management department.
Through this project, E.On aims to:
As-Is analysis of end-to-end processes and data flows
Recommendations covering systems, data structures, interfaces, and processes as well as detailed to-be-concepts
3 strategic objectives
  Standardised P&L Reconciliation Framework
  Strong Automation of the IFRS Closing Process
  Monthly IFRS Financial Statements
 Development of comprehensive target operating model, recon framework blueprint and implementation roadmap
Increasing complexity, margin pressure and acquisition activity stress the importance of seamless dataflows

## Slide 5: Our understanding of energy trading data flows
Realized Process
Processing data from ETRM system through to ERP system can be complex
Data Input
Exchange trades
Broker feeds
Other OTC
Unrealized Process
ETRM
(e.g., Allegro)
Interfaces
Manual data entry
Database
(e.g., Snowflake)
EOD runs
(potentially additional daily runs)
External parallel deal maintenance
(e.g., PPAs)
Manual upload
Decision on which purpose the database needs to fulfill
Consistency of data in the ETRM System needs to be ensured
Risk P&L
Including Risk specific adjustments
Financial Statement
Derivative reports
ERP
(e.g., SAP)
Recon for identification of Accruals
Establish Dataconsistency between ERP and Database for already settled deals
Accuracy of Deal-Inputs through Confirmation/Reconciliation Controls
Risk adjustments not relevant for accounting need to be excluded from dataflow
Front Office/ Risk & Performance Controlling
Accounting
Risk Adjustments relevant for accounting need to be included into dataflow
Enrichment of data with accounting relevant information – Own use / Fair Value Flag, IFRS 13 Adjustments, SAP Accounts
Interface for realised settled transactions – covering 11 Months of the year
Legend:
Critical reconciliations along dataflow
Accuracy of Settlement through implemented invoice reconciliation
Price Curve Storage
Completeness and accuracy of price curve data flow via regular external benchmarking and plausibility checks
Zielbild mit Key Points – State of the art definition

## Slide 6: Project Approach at a Glance
Impact Analysis
Organizational structure
Impact Assessment
Detailed Analysis
Recommendation
Roadmap & Alignment
Identification of activities affected by the scope of IFRS 20, considering country-specific regulatory regimes and type of businesses such as electricity and gas grid.
Work Packages
Activities
Deliverables
Impact Assessment for the in-scope entities, e.g. whether relationships between PPE and RAB are direct or indirect, impact of discounting.
Impacts on consolidation systems, asset management systems and regulatory accounting systems as well as general ledger, such as SAP-FI or Tagetik (consolidation).
Proposed implementation approach for affected entities.
Define a target system setup and required system changes to ensure well structured implementation.
Finalize cross-functional collaboration between IFRS accounting and regulatory experts.
Continuous project management to discuss and align project results and decide and approve on target solutions. Coordinate group-wide alignment across regulatory frameworks.
Our target: to provide you with clear recommendations for each country
Overview of affected entities (countries) and activities.
Defined milestones for the detailed analysis phase.
Documented assessment of accounting and system impacts (including analysis of PPE–RAB relationships).
Cross-functional alignment framework.
Aligned IFRS accounting and regulatory concept across jurisdictions.
Target process, system design and implementation roadmap.
Detailed implementation timeline, structure, resources and milestone plan.
Documentation of critical areas of IFRS 20 for E.ON (incl. initial solutions).
~1 week
~4 week
~1 week
~2 week

## Slide 7: Project Approach at a Glance
Our target: to provide you with clear recommendations for each country
Conduct knowledge transfer sessions with internal finance, risk Controlling, and IT teams
Phase 1(4-6 w): As-Is Analysis & Documentation
Sep
Oct (KW 40 - 44)
Dec (KW 49 - 53)
Work Packages
Key stakeholder Interviews
Targeted industry benchmarking
Develop TOM
1.1
2.1
2.2
Derive improvement measures for systems, data structures, interfaces, and processes
2.4
3.1
Key Outputs
As-is analysis report (process maps, data flow diagrams, gap analysis, root cause overview)
Reconciliation Framework Blueprint
Target-State Design Document
Documentation & handover meetings
Nov (KW 44 - 49)
40
41
42
43
44
45
46
47
48
49
50
51
Identification of weaknesses and improvement opportunities
1.2
1.3
Phase 3: Handover & Knowledge Transfer
Phase 2 (6-8 w): Target State Design & Recommendations
Structured walkthroughs of end-to-end processes and data flows from trading
source systems into risk and Performance Controlling P&L on the one hand, as well as into SAP and financial reporting on the other hand.
Quantitative analysis (potentially using Process Bionics).
Gap analysis between As-is report, Benchmarking & TOM
2.3
Implementation Roadmap
Executive Board Presentation
Business Case Development
2.5
Jan (KW 53 - 4)
52
53
1
2
3
4
5
6
7
8
9
10
11
12
13
Feb (KW 4 - 9)
Mar (KW 9 – 13 )

## Slide 8: Impact Analysis | Details
Proposed Deloitte Deliverables & Sign Offs
Key Challenges
Comprehensive impact and scope assessment covering affected activities (please see exemplary slides 11 and 12 for more details).
Initial accounting assessment and position paper, including preliminary conclusions on PPE–RAB relationships.
High-level overview of impacted systems and identified implementation risks (e.g. in tabular form).
High complexity driven by heterogeneous regulatory frameworks and country-specific regulations.
Fragmented and locally customized system landscapes, making a consistent impact assessment and comparability across entities challenging.
Identification and alignment of dependent E.ON Group projects requiring adaptation due to IFRS 20 (e.g. OPRES).
We provide transparency on accounting and system implications to define a clear and robust project scope
Identify all affected business activities across countries taking into account the complexity of the group structure and regulatory regimes.
Perform country-based workshops, including an initial assessment of how IFRS 20 impacts and conclude a preliminary evaluation of direct and indirect relationships between PPE and RAB.
Analyze high-level impacts on finance, regulatory (e.g. ETS) and reporting systems, including consolidation solution (e.g. Tagetik), asset management systems and local general ledger environments (e.g. SAP FI/ IFRS).
Define clear assumptions, dependencies and milestones to pave the way for the detailed analysis phase.
Deloitte activities
8
Deloitte for E.ON

## Slide 9: Organizational Structure | Details
We establish a robust governance and alignment model to ensure effective cross-functional collaboration and a coordinated group-wide IFRS 20 implementation
Proposed Deloitte Deliverables & Sign Offs
Challenges
Defined project governance and operating model, incl. workstream structure and responsibilities.
Roles and responsibilities matrix for key accounting, regulatory and cross-functional stakeholders.
Aligned roadmap and coordination framework to guide subsequent phases as well as documentation of critical areas of IFRS 20.
Coordination of multiple stakeholders with different functional perspectives, priorities and regulatory backgrounds.
Risk of unclear responsibilities and overlapping ownership between accounting, regulatory and IT functions.
Ensuring consistent alignment and decision-making across countries with differing regulatory frameworks and maturity levels.
Maintaining momentum and commitment across the Group while transitioning from analysis to execution.
Design and set up the overall project governance, including steering bodies, workstreams and clear decision-making structures.
Define roles and responsibilities for all workstreams and the interaction between IFRS accounting, regulatory experts and IT functions.
Establish effective collaboration and communication mechanisms to ensure consistent coordination across countries.
Develop a high-level roadmap and alignment approach to steer subsequent solution design and implementation activities.
Deloitte activities
9
9
Deloitte for E.ON

## Slide 10: Impact Analysis | Impact Assessment
Power | In IFRS 20 scope?
 | Direct or indirect relationship?
 | Are regulatory assets and liabilities expected and what are main sources?
Gas | In IFRS 20 scope?
 | Direct or indirect relationship?
 | Are regulatory assets and liabilities expected and what are main sources?
Heating | In IFRS 20 scope?
 | Direct or indirect relationship?
 | Are regulatory assets and liabilities expected and what are main sources?
Hydrogen | In IFRS 20 scope?
 | Direct or indirect relationship?
 | Are regulatory assets and liabilities expected and what are main sources?
Major assessment criteria considering country-specific regulations
Are regulatory regimes in scope of IFRS 20?
Here, we investigate the regulatory basis for each country and business: Are rates regulated? Does it create timing differences between IFRS 15 revenue and total allowed compensation?
This is expected to be met for power and gas in all countries.
Heating – at least in Germany – may not classify as regulation but price oversight. Hydrogen may be in scope later, but not now.
Evaluate whether the regulatory regime features a direct or indirect relationship between IFRS PPE and the regulated asset base
Does the regulatory agreement link the allowed compensation to identifiable underlying items?
Can the entity track items by amount and reporting period?
Analyze regulatory agreement and current accounting practice for expected sources of regulatory assets and liabilities
Are volume differences typical to exist and what has been the magnitude of these in the past?
Are actual costs expected to differ materially from those assumed in rate setting?
Does the entity have a significant amount of assets under construction? Does is currently capitalize interest on these projects as per IAS 23? If not, why?
What questions underlie the evaluation criteria?
Evaluation Criteria for IFRS 20 impact assessment

## Slide 11: Impact Analysis | Country Assessment
We receive E.ON accounting and regulatory documents per country.
We use AI to draft a preliminary assessment of criteria.
Deloitte accounting and regulatory experts (both our German team as well as Country Specific Experts) sense-check these drafts.
In the workshops, we will jointly validate and refine the assessment criteria.
Based on the agreed framework, the target countries will be assessed consistently across all businesses.
Upon request, further local Deloitte experts can be involved in the workshop, the country assessments, and the development of the final recommendations.
power | a) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
 | b) | Direct | Direct | Indirect | Indirect | Indirect | Indirect | Direct | Indirect
 | c) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Gas | a) | – | Yes | – | – | Yes | Yes | Yes | –
 | b) | – | Direct | – | – | Indirect | Indirect | Direct | –
 | c) | – | Yes | – | – | Yes | Yes | Yes | –
Country impact assessment based on criteria jointly defined with E.ON
Country-Specific Evaluation
Power | a) In IFRS 20 scope? | Yes
 | b) Direct or indirect relationship? | Direct
 | c) Are regulatory assets and liabilities expected and what are main sources? | Yes
Gas | a) In IFRS 20 scope? | Yes
 | b) Direct or indirect relationship? | Direct
 | c) Are regulatory assets and liabilities expected and what are main sources? | Yes
Heating | a) In IFRS 20 scope? | No
 | b) Direct or indirect relationship? | N/A
 | c) Are regulatory assets and liabilities expected and what are main sources? | N/A
Hydro-gen | a) In IFRS 20 scope? | No
 | b) Direct or indirect relationship? | N/A
 | c) Are regulatory assets and liabilities expected and what are main sources? | N/A
Deloitte (pre-)assessment criteria
Are regulatory regimes in scope of IFRS 20?
Power and gas networks are regulated by the Energy Law (EnWG), incentive regulation (ARegV) currently, and prospectively BNetzA framework decisions.
The regulator sets an allowed revenue (Erlösobergrenze).
Timing differences are compensated via the regulatory account (or Regulierungskonto).
Evaluate whether the regulatory regime features a direct or indirect relationship between IFRS property, plant and equipment and the regulated asset base?
The RAB is defined based on statutory assets.
Differences to IFRS PPE may exist but should be trackable.
Analyze regulatory agreement and current accounting practice for expected sources of regulatory assets and liabilities
Forecast vs actual network usage.
Non-controllable costs that are higher or lower than expected.
Shorter regulatory depreciation of gas networks.
Country-Specific Approach
Initial (pre-)assessment based on public information and AI